Template note — delete before sending: Send within 24 hours of the kickoff call, with the 90-day plan pages at the back for sign-off (signed within 5 days). The approver attending kickoff is a gate, not a preference — if they didn't attend, move the meeting rather than send this. Each service line has two plan pages — at a glance for the client, then in depth — keep both for every service line this client bought and delete the rest. Custom projects use the project plan pages.

CLIENT ONBOARDING  ·  INTAKE RECAP

Your intake recap

What you told us, what we found, what we agreed at kickoff — and your 90-day plan to sign.

| CLIENT | [Client] | KICKOFF | [date] |
| --- | --- | --- | --- |
| YOUR TEAM | [Names] — including [Approver] | OPES TEAM | [Account Lead name], [Strategist name] |
| RECAP SENT | [date — within 24 hours of kickoff] | PLAN SIGNED BY | [date — within 5 days] |

# 01  What you told us

From your intake questionnaire and our conversation at kickoff. If anything here is wrong, tell us in #[client]-opes — it shapes everything that follows.

| Your business | [What you sell, who to, and where] |
| --- | --- |
| Your customers | [Who buys, how often, and why] |
| Where revenue comes from today | [Channels and rough split] |
| Tools you use | [Platforms and systems] |
| What's working | [In your words] |
| What isn't | [In your words] |
| What we need to work around | [Budget, brand rules, legal, busy periods, other agencies] |

# 02  The one number

We agreed one number, not a list. It's the number our work is measured against, and it's how we keep the scope focused.

| The metric | [e.g. email's share of online revenue] |
| --- | --- |
| Where it is today | [Baseline, and where the figure comes from] |
| Target | [Target] |
| By | [date] |
| Measured in | [e.g. Klaviyo and Shopify reports] |
| Reported | Every Thursday, in your weekly update |

Template note — delete before sending: Ask for sign-off on the number in the channel: “Please reply ‘agreed’ by [date], or tell us what's wrong.”

# 03  What your Growth Audit found

| BASELINE SCORE [ ] / 100 From your walkthrough on [date] | TARGET 90 / 100 By month three — [date] | RE-SCORES Day 60 · 90 [date] and [date] |
| --- | --- | --- |

## The three things that move it most

- [Finding — written as ‘X is costing you Y’]

- [Finding]

- [Finding]

| Fixed within your package | Would be an addition — quoted separately |
| --- | --- |
| [Item] [Item] [Item] | [Item — with a price and a date] [Item] |

# 04  Timeline, milestones and dependencies

The key dates from your 90-day plan. Each one names who owns it, and what it depends on from your side.

| Milestone | Date | Opes owner | Depends on (your side) |
| --- | --- | --- | --- |
| [Milestone] | [date] | [Name] | [Name — what, by when] |
| [Milestone] | [date] | [Name] | [Name — what, by when] |
| [Milestone] | [date] | [Name] | [Name — what, by when] |
| Growth Audit re-score | [Day 60 date] | [Strategist name] | [Approver] attends (30 minutes) |
| Graduation review | [Day 90 date] | [Account Lead name] | [Approver] attends (45 minutes) |

# 05  Who does what

| Name | Role | Responsible for |
| --- | --- | --- |
| [Account Lead name] | Account Lead, Opes | Your plan, your results, and anything that's stuck |
| [Strategist name] | Strategist, Opes | Your Growth Audit, the plan sequence and what we test |
| [Account Coordinator name] | Account Coordinator, Opes | Access, scheduling and your weekly update |
| [Approver] | [Role], [Client] | Signs off decisions and the 90-day plan |
| [Client contact] | [Role], [Client] | Day-to-day contact, approvals within 48 hours |

# 06  How we'll work together

Agreed at kickoff.

| Channel | One shared Slack channel: #[client]-opes |
| --- | --- |
| Weekly update | Every Thursday in the channel, whether or not there's news |
| Our response time | A first response within 4 working hours |
| Your approvals | Within 48 hours — later approvals move the dates that depend on them |
| Meetings | [Cadence agreed at kickoff] |
| If something's stuck | [Account Lead name] first. Not resolved in 2 working days? [Director name], [email]. |

# 07  Risks, and what we'll do about them

| Risk | What we'll do | Owner |
| --- | --- | --- |
| Access delays hold up the audit fixes | Requests staged and chased every 48 hours, escalating to [Account Lead name] on Day 7 | [Account Coordinator name] |
| Approvals slip during [busy period] | Approval dates agreed in the plan; a late approval moves the dates that depend on it | [Client contact] |
| [Risk raised at kickoff] | [What we'll do] | [Name] |

# 08  What month one looks like

Stability, not lift. Month one is about stability and fixing foundations. We target improvement from month two.

# 09  Next steps

| What we'll do | Owner | By |
| --- | --- | --- |
| [Action] | [Name] | [date] |
| [Action] | [Name] | [date] |
| [Action] | [Name] | [date] |

YOUR ONE ACTION [Approver]: [the single action agreed at kickoff — e.g. sign the 90-day plan below by [date]].

Your 90-day plan at a glance

Retention & Lifecycle Email  ·  [Client]  ·  Day 1: [date]  ·  The one number: [metric, baseline → target]  ·  Growth Audit: [baseline] → 90

|  | MONTH 1 · DAYS 1–30 Fix the foundations | MONTH 2 · DAYS 31–60 Build what earns | MONTH 3 · DAYS 61–90 Grow and prove it |
| --- | --- | --- | --- |
| What we do | - Authenticate your sending domain and warm up sending - Check your tracking and clean your list - Build your welcome, abandoned cart and abandoned checkout flows | - Build post-purchase, browse abandonment and sunset flows - Set up your five core customer segments | - Run a planned campaign calendar [and SMS, if in scope] - Test, and check flow revenue against a holdout group |
| What you'll see | - Your Growth Audit baseline score - Your first flow live by the end of week 4 | - Six flows live and earning - Your Day 60 Growth Audit re-score | - Test results and your Day 90 report - Your graduation review — aiming for 90 |
| What we need from you | - DNS records added within 48 hours of our request - Brand assets and discount rules - Approvals within 48 hours | - Review and product data - Your VIP and customer definitions | - Your promotions calendar - [Approver] at the Day 90 review |

| The finish line Onboarding ends when all of these are true. | - Growth Audit re-score of 90 or above - Core and secondary flows live, each meeting the acceptance criteria agreed before it was built - The one number at or above [target] | - Deliverability healthy for 30 days - Reporting handed over and reviewed with [Approver] |
| --- | --- | --- |

| Plan agreed | [Approver], for [Client] · signature and date | [Account Lead], for Opes Consulting · signature and date |
| --- | --- | --- |

Your 90-day plan in depth

Retention & Lifecycle Email  ·  every step, who owns it, and what it needs from you

|  | Month 1 |  | Month 2 |  | Month 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What happens | 1–15 | 16–30 | 31–45 | 46–60 | 61–75 | 76–90 | What you'll see · who owns it | What it needs from you |
| Deliverability Days 1–21 · SPF, DKIM, DMARC and warm-up |  |  |  |  |  |  | Domain authenticated and passing Owner: [Strategist] | [Name] adds DNS records within 48 hours of our request |
| Integration and tracking Days 1–21 · Store connection and key events |  |  |  |  |  |  | Key events verified Owner: [Integrations Specialist] | [Name] accepts Shopify and Klaviyo access by [Day 4 date] |
| List hygiene Days 1–14 · Suppression and consent checks |  |  |  |  |  |  | A clean, consented sending list Owner: [Strategist] | [Name] approves suppression rules within 48 hours |
| Core flows Days 15–30 · Welcome, cart and checkout |  |  |  |  |  |  | Three core flows live, the first by week 4 Owner: [Strategist] | [Name] confirms brand assets and discount rules by [Day 12 date] |
| Secondary flows Days 31–45 · Post-purchase, browse, sunset |  |  |  |  |  |  | Three secondary flows live Owner: [Strategist] | [Name] shares review and product data by [Day 30 date] |
| Segmentation Days 46–60 · Five core customer segments |  |  |  |  |  |  | Segments used on every send Owner: [Strategist] | [Name] confirms VIP definitions by [Day 45 date] |
| SMS and campaigns Days 61–75 · Campaigns [and SMS, if in scope] |  |  |  |  |  |  | Campaign calendar running Owner: [Strategist] | [Name] shares the promotions calendar by [Day 55 date] |
| Optimisation and reporting Days 76–90 · Testing, holdout check, reporting |  |  |  |  |  |  | Test results and Day 90 report Owner: [Account Lead] | [Approver] attends the Day 90 review |
| Your top 3 audit fixes [Days] · [Fix 1] · [Fix 2] · [Fix 3] |  | ◆ | ◆ | ◆ |  |  | Each fix reported in your weekly update Owner: [Strategist] | [Name — anything the fixes need, by when] |
| Growth Audit re-scores Days 60 and 90 · Same checklist, same standards |  |  |  | ◆ |  | ◆ | Your score against the 90 target Owner: [Strategist] | [Approver] joins both (30 minutes each) |

■ We're working on it        ■ Only if you choose it        ◆ Milestone        ■ Needed from you

Your 90-day plan at a glance

HubSpot & CRM Integration  ·  [Client]  ·  Day 1: [date]  ·  The one number: [metric, baseline → target]  ·  Growth Audit: [baseline] → 90

|  | MONTH 1 · DAYS 1–30 Set up and design | MONTH 2 · DAYS 31–60 Get the team using it | MONTH 3 · DAYS 61–90 Make it stick |
| --- | --- | --- | --- |
| What we do | - Configure HubSpot: users, properties, pipelines and domains - Clean and migrate your data - Map your sales process with your team | - Train every rep on real deals - Connect every inbox and calendar - Start tracking adoption every week | - Reinforce the process wherever adoption slips - Run pipeline reviews from HubSpot |
| What you'll see | - Your Growth Audit baseline score - A configured portal and a signed-off sales process | - Every rep trained - Your Day 60 Growth Audit re-score | - A weekly adoption report - Your graduation review — rep adherence above 70% |
| What we need from you | - Super Admin access and your CRM export - Your sales leader and two reps at two workshops | - Each rep books a session and connects their inbox | - Your sales leader runs the weekly pipeline review in HubSpot |

| The finish line Onboarding ends when all of these are true. | - Rep adherence above 70% — reps logging activity, updating deals and setting next steps every week - Growth Audit re-score of 90 or above | - The leadership dashboard used in the weekly pipeline review - Data quality holding: duplicates under 2%, required fields complete |
| --- | --- | --- |

| Plan agreed | [Approver], for [Client] · signature and date | [Account Lead], for Opes Consulting · signature and date |
| --- | --- | --- |

Your 90-day plan in depth

HubSpot & CRM Integration  ·  every step, who owns it, and what it needs from you

|  | Month 1 |  | Month 2 |  | Month 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What happens | 1–15 | 16–30 | 31–45 | 46–60 | 61–75 | 76–90 | What you'll see · who owns it | What it needs from you |
| Portal configuration Weeks 1–4 · Set-up and data migration |  |  |  |  |  |  | A configured portal with clean data Owner: [HubSpot Specialist] | [Name] grants Super Admin and sends the CRM export by [Day 4 date] |
| Process design Weeks 1–4 · Mapping how your team really sells |  |  |  |  |  |  | A signed-off sales process and stage criteria Owner: [Strategist] | [Sales leader] and two reps join two workshops by [Day 21 date] |
| Rep onboarding Weeks 4–6 · Training on real deals |  |  |  |  |  |  | Every rep trained and connected Owner: [HubSpot Specialist] | Each rep books a session and connects their inbox by [Day 35 date] |
| Measure and reinforce Month 2 onwards · Weekly adoption tracking |  |  |  |  |  |  | A weekly adoption report Owner: [Account Lead] | [Sales leader] runs the weekly pipeline review from HubSpot |
| Your top 3 audit fixes [Days] · [Fix 1] · [Fix 2] · [Fix 3] |  | ◆ | ◆ | ◆ |  |  | Each fix reported in your weekly update Owner: [HubSpot Specialist] | [Name — anything the fixes need, by when] |
| Growth Audit re-scores Days 60 and 90 · Same checklist, same standards |  |  |  | ◆ |  | ◆ | Your score against the 90 target Owner: [Strategist] | [Approver] joins both (30 minutes each) |
| Graduation gate Day 90 · Rep adherence above 70% |  |  |  |  |  | ◆ | An adherence report Owner: [Account Lead] | [Sales leader] confirms the adherence figures |

■ We're working on it        ■ Only if you choose it        ◆ Milestone        ■ Needed from you

Your 90-day plan at a glance

Meta Management & Marketing  ·  [Client]  ·  Day 1: [date]  ·  The one number: [metric, baseline → target]  ·  Growth Audit: [baseline] → 90

|  | MONTH 1 · DAYS 1–30 Hold steady, fix tracking | MONTH 2 · DAYS 31–60 Improve | MONTH 3 · DAYS 61–90 Scale what worked |
| --- | --- | --- | --- |
| What we do | - Check your pixel and Conversions API - Restructure the account where the audit shows it's needed - Build your creative pipeline | - Test new concepts and audiences - Move budget to what's working | - Put more spend and volume behind proven ads |
| What you'll see | - Your Growth Audit baseline score - Current performance held steady - Your first batch of new ads live | - Test results in every weekly update - Your Day 60 Growth Audit re-score | - Scaled winners and your Day 90 report - Your graduation review — aiming for 90 |
| What we need from you | - Partner access by Day 3 - Brand assets, product shots and UGC permissions | - Approval on new concepts within 48 hours - A budget decision at the Day 60 review | - [Approver] at the Day 90 review |

| The finish line Onboarding ends when all of these are true. | - Growth Audit re-score of 90 or above - Tracking verified: Conversions API live, Purchase event quality Good or better | - ROAS and CAC at or better than [target] for the final 30 days - The creative pipeline running at the agreed volume |
| --- | --- | --- |

| Plan agreed | [Approver], for [Client] · signature and date | [Account Lead], for Opes Consulting · signature and date |
| --- | --- | --- |

Your 90-day plan in depth

Meta Management & Marketing  ·  every step, who owns it, and what it needs from you

|  | Month 1 |  | Month 2 |  | Month 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What happens | 1–15 | 16–30 | 31–45 | 46–60 | 61–75 | 76–90 | What you'll see · who owns it | What it needs from you |
| Access, tracking and baseline Days 1–15 · Partner access, pixel and Conversions API |  |  |  |  |  |  | Tracking verified, baseline recorded Owner: [Strategist] | [Name] adds Opes as a partner by [Day 3 date] |
| Audit and restructure Days 1–30 · Goal: maintain current performance |  |  |  |  |  |  | A restructured account Owner: [Strategist] | [Approver] attends the audit walkthrough |
| Creative pipeline Days 1–30 · Static, video and UGC-style ads |  |  |  |  |  |  | The first batch of new ads live Owner: [Strategist] | [Name] sends assets and UGC permissions by [Day 7 date] |
| Improvement Days 31–60 · Testing concepts and audiences |  |  |  |  |  |  | Budget moved to what works Owner: [Strategist] | [Name] approves new concepts within 48 hours |
| Scale what worked Days 61–90 · More spend behind proven ads |  |  |  |  |  |  | Scaled winners and Day 90 report Owner: [Account Lead] | [Approver] decides on budget at the Day 60 review |
| Your top 3 audit fixes [Days] · [Fix 1] · [Fix 2] · [Fix 3] | ◆ | ◆ | ◆ |  |  |  | Each fix reported in your weekly update Owner: [Strategist] | [Name — anything the fixes need, by when] |
| Growth Audit re-scores Days 60 and 90 · Same checklist, same standards |  |  |  | ◆ |  | ◆ | Your score against the 90 target Owner: [Strategist] | [Approver] joins both (30 minutes each) |

■ We're working on it        ■ Only if you choose it        ◆ Milestone        ■ Needed from you

Your 90-day plan at a glance

Sales Team Integration  ·  [Client]  ·  Day 1: [date]  ·  The one number: [metric, baseline → target]  ·  Growth Audit: [baseline] → 90

|  | MONTH 1 · DAYS 1–30 Tier 1: Sales Call Optimisation | MONTH 2 · DAYS 31–60 · ONLY IF YOU CHOOSE IT Tier 2: Email Automation & VSL | MONTH 3 · DAYS 61–90 · ONLY IF YOU CHOOSE IT Tier 3: Enhanced Sales Team |
| --- | --- | --- | --- |
| What we do | - Review your recorded sales calls - Rebuild your call structure and objection library - Coach your reps every week | - Automate your follow-up - Script and record your video sales letter | - Plan your team expansion - Hiring scorecards and onboarding for new reps |
| What you'll see | - Your Growth Audit baseline score - Tier 1 results on Day 30 — then you decide | - Follow-up automation live - Your Day 60 re-score, and the Tier 3 decision | - An expansion plan - Your graduation review — aiming for 90 |
| What we need from you | - Recordings and recording consent by Day 3 - Your reps at weekly coaching | - The VSL recorded by Day 50 | - A decision on hiring budget |

| The finish line Onboarding ends when all of these are true. | - Growth Audit re-score of 90 or above - The new call structure used on 8 or more calls in 10 | - A written follow-up within 24 hours on 8 or more calls in 10 - Close and show rates measured against your baseline over the full lab |
| --- | --- | --- |

| Plan agreed | [Approver], for [Client] · signature and date | [Account Lead], for Opes Consulting · signature and date |
| --- | --- | --- |

Your 90-day plan in depth

Sales Team Integration  ·  every step, who owns it, and what it needs from you

|  | Month 1 |  | Month 2 |  | Month 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What happens | 1–15 | 16–30 | 31–45 | 46–60 | 61–75 | 76–90 | What you'll see · who owns it | What it needs from you |
| Tier 1 — Sales Call Optimisation Days 1–30 · Call reviews and coaching |  |  |  |  |  |  | A new call structure and [x] coaching sessions Owner: [Strategist] | [Name] shares recordings and confirms consent by [Day 3 date] |
| Decision: Tier 2, or stop Day 30 · Results reviewed against your baseline |  | ◆ |  |  |  |  | Written Tier 1 results Owner: [Account Lead] | [Approver] decides by [Day 35 date] |
| Tier 2 — Email Automation & VSL Days 31–60 · Only if you choose it |  |  |  |  |  |  | Follow-up automation live, VSL recorded Owner: [Strategist] | [Name] records the VSL by [Day 50 date] |
| Decision: Tier 3 Day 60 · A separate decision |  |  |  | ◆ |  |  | Written Tier 2 results Owner: [Account Lead] | [Approver] decides by [Day 65 date] |
| Tier 3 — Enhanced Sales Team Days 61–90 · Only if you choose it |  |  |  |  |  |  | An expansion and onboarding plan Owner: [Account Lead] | [Approver] confirms hiring budget |
| Your top 3 audit fixes [Days] · [Fix 1] · [Fix 2] · [Fix 3] | ◆ | ◆ |  |  |  |  | Each fix reported in your weekly update Owner: [Strategist] | [Name — anything the fixes need, by when] |
| Growth Audit re-scores Days 60 and 90 · Same checklist, same standards |  |  |  | ◆ |  | ◆ | Your score against the 90 target Owner: [Strategist] | [Approver] joins both (30 minutes each) |

■ We're working on it        ■ Only if you choose it        ◆ Milestone        ■ Needed from you

Your project plan at a glance

Custom projects — websites, automations and integrations  ·  [Project name]  ·  Launch date: [date]

|  | STAGE 1 Scope [Week 1] | STAGE 2 Design [Weeks 2–3] | STAGE 3 Build [Weeks 3–5] | STAGE 4 Test [Week 6] | STAGE 5 Launch [Week 7] | STAGE 6 Handover [Weeks 7–9] |
| --- | --- | --- | --- | --- | --- | --- |
| What happens | - We map what's needed, how it connects and what could go wrong | - We design the pages or the automation flow | - We build it in a test space — nothing touches your live systems | - We test against the checklist agreed before building | - We go live at a time agreed with you | - We show you how it works and support you for [14] days |
| What you get | - A Technical Scoping Document with a fixed scope | - Designs or an automation map to approve | - A test link or workspace to try | - A test log you can check | - Your live site or automations | - A how-it-works guide and a credentials list |
| What we need from you | - Access to your systems - Sign-off on the scope | - Design approval within 48 hours | - Answers to build questions within 48 hours | - Sign-off on testing | - Go-live approval | - Confirmation that handover is complete |

| The finish line The project is complete when all of these are true. | - Everything in the signed scope is live and passes its agreed checks - Your credentials are stored in your own systems | - You have the how-it-works guide, and support has closed - Changes after sign-off are quoted before any work starts |
| --- | --- | --- |

If an approval is late, every later date — including launch — moves back by the same number of working days, and we'll tell you which dates moved and why.

Your project plan in depth

Custom projects  ·  [Project name]  ·  every milestone, who owns it, and who signs it off

| # | Milestone | What you get | Opes owner | Your sign-off | Sign-off by | Target date |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Scope signed off | Technical Scoping Document v1.0 | [Account Lead] | [Approver] signs the scope | [date] | [date] |
| 2 | Design approved | [Designs / automation map] | [Integrations Specialist] | [Approver] approves the design | [date] | [date] |
| 3 | Build complete in test | [Test link / test workspace] | [Integrations Specialist] | No sign-off — progress shared in #[client]-opes | [date] | [date] |
| 4 | Testing signed off | Test log against the agreed checks | [Integrations Specialist] | [Approver] signs off testing | [date] | [date] |
| 5 | Launch | [Live site / live automations] | [Integrations Specialist] | [Approver] gives go-live approval | [date] | [date] |
| 6 | Handover complete | Guide, credentials list, [14] days' support | [Account Lead] | [Approver] confirms handover | [date] | [date] |

If an approval is late, every later date — including launch — moves back by the same number of working days. [Account Lead] confirms the new dates in #[client]-opes the same day.

| Plan agreed | [Approver], for [Client] · signature and date | [Account Lead], for Opes Consulting · signature and date |
| --- | --- | --- |